## motamaze mvp - project plan
MotaMaze MVP - Project Plan |  | This spreadsheet was created using monday.com
Group Title |  | Try it free →
Name | Subitems | Workstream | Assigned | Assigned | Status | RAG | Critical Path | Timeline - Start | Timeline - End | Dependency | Started On | Finalized On | Comments (done / pending) | Item ID (auto generated)
Project plan, milestones & RACI agreed (this workbook) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | In Progress | Amber | ★ CRITICAL | 2026-06-15 | 2026-06-17 |  | 2026-06-14 |  |  | 12272268103
Client<->Backend REST API contract (endpoints, payloads, JWT, error codes) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | In Progress | Amber | ★ CRITICAL | 2026-06-19 | 2026-06-24 | Project plan, milestones & RACI agreed (this workbook) | 2026-06-14 |  | DONE: data model defined (Firestore collections, ConfigService/MatchResultService plan, Remote Config + Firestore→BigQuery direction). PENDING: Saul to derive the REST contract from it — endpoint list, request/response payloads, JWT/auth header spec, error taxonomy — then circulate for review. | 12272268104
Environment & secrets design sign-off (dev/staging/prod topology) |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-18 | 2026-06-18 | Project plan, milestones & RACI agreed (this workbook) |  |  |  | 12272268105
GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  | Infra/DevOps | Saul | Saul Zavala Morin | Done | Blue |  | 2026-06-10 | 2026-06-13 |  |  | 2026-06-04 | DONE (by Juan): Firestore, BigQuery, Cloud Storage, Cloud IAM, service account game-api-backend, ADC impersonation, budget alerts. PENDING for Saul: RS256 keys, Cloud Run deploy, env split. | 12272254517
FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  | Backend Foundation | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-25 | 2026-06-26 | Client<->Backend REST API contract (endpoints, payloads, JWT, error codes), GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  |  |  | 12272254518
RS256 keypair in Secret Manager + JWKS (.well-known) endpoint |  | Backend Foundation | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-29 | 2026-06-29 | FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  |  |  | 12272254519
Firestore users/sessions/revoked_jtis schema + Production-mode rules |  | Backend Foundation | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-29 | 2026-06-30 | FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  |  |  | 12272254520
Dev / Staging / Prod environments (project-per-env) + Terraform module |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-27 | 2026-06-28 | FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks), Environment & secrets design sign-off (dev/staging/prod topology) |  |  |  | 12272254521
CI/CD: GitHub Actions + Artifact Registry single-image promotion pipeline |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-02 | 2026-07-03 | Dev / Staging / Prod environments (project-per-env) + Terraform module |  |  |  | 12272268267
Cloud Monitoring/alerts (5xx on auth & payments), logging, uptime, Pub/Sub kill switch |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-01 | 2026-07-02 | FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  |  |  | 12272268268
POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-06 | 2026-07-07 | RS256 keypair in Secret Manager + JWKS (.well-known) endpoint, Firestore users/sessions/revoked_jtis schema + Production-mode rules |  |  |  | 12272268269
/auth/refresh rotation + /auth/logout + JTI revocation; pending-callback poll |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-10 | 2026-07-13 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272121944
DELETE /auth/account — full erase + BigQuery deletion queue (GDPR / Apple 5.1.1) |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-14 | 2026-07-15 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions), POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272121945
HTTPS App Links (assetlinks.json) / Universal Links (AASA) hosting for OAuth callback |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-14 | 2026-07-14 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272121946
Backend /progress + POST /progress/level-complete (server-validated unlock/score) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-15 | 2026-07-16 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair, Firestore users/sessions/revoked_jtis schema + Production-mode rules |  |  |  | 12272122018
Backend /lives (server-authoritative regen) + /lives/spend + config — Anexo §4 |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-16 | 2026-07-17 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair, Firestore users/sessions/revoked_jtis schema + Production-mode rules |  |  |  | 12272122019
Backend /lives/grant (iap / rewarded_ad SSV / promo) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-23 | 2026-07-24 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator, Backend /lives (server-authoritative regen) + /lives/spend + config — Anexo §4 |  |  |  | 12272122020
Backend /store/catalog + promotions (server-resolved, audience-segmented) — Anexo §5 |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-23 | 2026-07-24 | Firestore users/sessions/revoked_jtis schema + Production-mode rules, Backend /progress + POST /progress/level-complete (server-validated unlock/score) |  |  |  | 12272133961
Backend /profile/equip-skin (entitlement-checked) + equipped_skin persistence |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-29 | 2026-07-29 | Backend /store/catalog + promotions (server-resolved, audience-segmented) — Anexo §5 |  |  |  | 12272254774
Remote Config for level/lives/catalog tunables (live-tunable, no app update) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-30 | 2026-07-31 | Backend /store/catalog + promotions (server-resolved, audience-segmented) — Anexo §5 |  |  |  | 12272254775
Enable Google Play Developer API (24h activation — Day 1) + Play Console SA invite |  | External Services | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-15 | 2026-06-15 | GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  |  |  | 12272254776
POST /payments/android/verify (verify -> grant -> acknowledge/consume, replay-safe) |  | Payments Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-07 | 2026-07-08 | Enable Google Play Developer API (24h activation — Day 1) + Play Console SA invite, Firestore users/sessions/revoked_jtis schema + Production-mode rules |  |  |  | 12272254777
Daily reconciliation job (Cloud Scheduler): pending verify + refund detection |  | Payments Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-20 | 2026-07-21 | POST /payments/android/verify (verify -> grant -> acknowledge/consume, replay-safe) |  |  |  | 12272254779
Refund notifications (Play Pub/Sub + Apple ASSN v2) endpoints |  | Payments Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-22 | 2026-07-22 | POST /payments/android/verify (verify -> grant -> acknowledge/consume, replay-safe) |  |  |  | 12272254780
AdMob account + ad units (rewarded/interstitial/banner) + test IDs |  | External Services | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-16 | 2026-06-17 | GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  |  |  | 12272254782
BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions) |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-18 | 2026-06-19 | GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  |  |  | 12272094753
Firestore -> BigQuery async streaming (off hot path) + dedup keys |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-22 | 2026-06-23 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions) |  |  |  | 12272094755
Ad-revenue reconciliation: custom impression event + AdMob Reporting API daily job |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-10 | 2026-07-13 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions), AdMob client integration + SDK init order (consent -> ATT -> init) via Services.ads |  |  |  | 12272094757
Looker Studio dashboards: retention, per-region/per-age revenue, KPI gates |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-02 | 2026-07-03 | Firestore -> BigQuery async streaming (off hot path) + dedup keys |  |  |  | 12272094760
Tenjin SDK integration (client) + backend fraud filtering (before first paid UA) |  | External Services | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-24 | 2026-06-26 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions) |  |  |  | 12272094807
Collect & synthesize feedback (survey + watch sessions) -> prioritized change list |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-08-19 | 2026-08-25 | Distribute mini-launch build (Play internal track / TestFlight) to testers |  |  |  | 12272094811
Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-17 | 2026-07-22 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272175643
Verifiable parental consent (email-plus) flow — backend + client UI |  | Compliance | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-08-05 | 2026-08-11 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags, Auth UI + Google sign-in client flow (OS.shell_open, callback poll) |  |  |  | 12272094534
Brazil age assurance: app-store/OS age signals (Apple Declared Age Range / Play) |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-23 | 2026-07-27 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  |  |  | 12272094535
CCPA opt-out: in-app UI + Firestore persistence + RDP flag in AdMob init |  | Compliance | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-08-05 | 2026-08-07 | AdMob client integration + SDK init order (consent -> ATT -> init) via Services.ads, Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  |  |  | 12272094536
Monthly recalc Cloud Function (age threshold crossing, per-user country) |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-27 | 2026-07-28 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  |  |  | 12272094537
Privacy Policy + Terms (EN + PT-BR) hosted; Data Safety + Privacy Nutrition labels |  | Compliance | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-07-23 | 2026-07-27 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  |  |  | 12272094538
IARC rating (globalratings.com) + ClassInd mapping (BR 'Livre') |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-30 | 2026-07-31 | Privacy Policy + Terms (EN + PT-BR) hosted; Data Safety + Privacy Nutrition labels |  |  |  | 12272094539
Alpha internal build + technical validation (Fase Alpha gate) |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-08-29 | 2026-09-01 | Firebase Test Lab runs on 30+ physical devices (crash-free gate), Pre-Alpha polish from playtest feedback (gameplay/onboarding/difficulty fixes), MP Go/No-Go gate - playtest (agreed metrics) |  |  |  | 12272094541
Upgrade Firebase to Blaze (2 weeks before launch) + prod secrets/bindings |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-09 | 2026-07-09 |  |  |  |  | 12272175997
Closed beta with Discord cohort (crash <1%, flows functional) — Beta gate |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-09 | 2026-09-17 | Android closed/open test tracks (Play Console) — Beta build, Stand up Discord server (structure per plan §4.1) + roles |  |  |  | 12272176000
Community insight pipeline: self-hosted model in tenant, de-identified aggregates |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-03 | 2026-07-06 | Stand up Discord server (structure per plan §4.1) + roles, Firestore -> BigQuery async streaming (off hot path) + dedup keys |  |  |  | 12272094736
Release Candidate build + critical-issue burn-down + operational validation |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-10 | 2026-09-13 | Alpha/Beta Go/No-Go gate (agreed metrics), Closed beta with Discord cohort (crash <1%, flows functional) — Beta gate |  |  |  | 12272094738
Soft launch LATAM (Brazil + Mexico) — production deploy |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-14 | 2026-09-18 | Release Candidate build + critical-issue burn-down + operational validation, Privacy Policy + Terms (EN + PT-BR) hosted; Data Safety + Privacy Nutrition labels, Upgrade Firebase to Blaze (2 weeks before launch) + prod secrets/bindings, Brazil age assurance: app-store/OS age signals (Apple Declared Age Range / Play) |  |  |  | 12272094740
Monitor kill-criteria (D1>=25-30%, D7>=10%, No-Ads 2-5%, LTV>cost) on dashboards |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-09-19 | 2026-09-25 | Soft launch LATAM (Brazil + Mexico) — production deploy, Looker Studio dashboards: retention, per-region/per-age revenue, KPI gates |  |  |  | 12272094744
Live balance/economy tuning via Remote Config (levels, lives, promotions) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-10-02 | 2026-10-07 | Remote Config for level/lives/catalog tunables (live-tunable, no app update), Soft launch LATAM (Brazil + Mexico) — production deploy |  |  |  | 12272094746
Stability + monetization + retention soft-launch testing (Fase Beta/Soft Launch) |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-25 | 2026-10-08 | Soft launch LATAM (Brazil + Mexico) — production deploy |  |  |  | 12272094748
Soft-launch kill-criteria review + go/no-go (LA EMPRESA discretion) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-10-20 | 2026-10-21 |  |  |  |  | 12272094750
Commercial launch readiness checklist sign-off (no-go items cleared) |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-10-22 | 2026-10-26 | Soft-launch kill-criteria review + go/no-go (LA EMPRESA discretion) |  |  |  | 12272094752
Official LATAM commercial launch (Fase 4) — full production release |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-10-27 | 2026-10-29 | Commercial launch readiness checklist sign-off (no-go items cleared) |  |  |  | 12272094754
Post-launch operations runbook + on-call (2-yr support obligation begins) |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-10-30 | 2026-10-30 | Official LATAM commercial launch (Fase 4) — full production release |  |  |  | 12272094756
Technical documentation pass (systems, integrations, architecture) — Anexo §7 |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-10-30 | 2026-11-04 |  |  |  |  | 12272094759
Alpha/Beta Go/No-Go gate (agreed metrics) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-18 | 2026-09-18 | Closed beta with Discord cohort (crash <1%, flows functional) — Beta gate |  |  |  | 12275380968
MP Go/No-Go gate - playtest (agreed metrics) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-08-28 | 2026-08-28 | Pre-Alpha polish from playtest feedback (gameplay/onboarding/difficulty fixes) |  |  |  | 12275387415
[8 empty] | 2026-06-10 | 2026-11-04 |  | 2026-06-14 | 2026-06-04