## motamaze mvp - project plan
MotaMaze MVP - Project Plan |  | This spreadsheet was created using monday.com
Group Title |  | Try it free →
Name | Subitems | Workstream | Assigned | Assigned | Status | RAG | Critical Path | Timeline - Start | Timeline - End | Dependency | Started On | Finalized On | Comments (done / pending) | Item ID (auto generated)
Project plan, milestones & RACI agreed (this workbook) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | In Progress | Amber | ★ CRITICAL | 2026-06-15 | 2026-06-17 |  | 2026-06-14 |  |  | 12272268103
Client<->Backend REST API contract (endpoints, payloads, JWT, error codes) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | In Progress | Amber | ★ CRITICAL | 2026-06-19 | 2026-06-24 | Project plan, milestones & RACI agreed (this workbook) | 2026-06-14 |  | DONE: data model defined (Firestore collections, ConfigService/MatchResultService plan, Remote Config + Firestore→BigQuery direction). PENDING: Saul to derive the REST contract from it — endpoint list, request/response payloads, JWT/auth header spec, error taxonomy — then circulate for review. | 12272268104
Environment & secrets design sign-off (dev/staging/prod topology) |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-18 | 2026-06-18 | Project plan, milestones & RACI agreed (this workbook) |  |  |  | 12272268105
Client infra layer: Events bus, Services locator, resources, node FSM |  | Client Foundation | Juan | Juan Mosqueda | Done | Blue |  | 2026-06-01 | 2026-06-12 |  |  | 2026-06-12 | DONE: Events bus + Services locator + resource classes + node FSM (Step 0). | 12272268106
Graph-based procedural maze generation (perfect maze) |  | Gameplay | Juan | Juan Mosqueda | Done | Blue | ★ CRITICAL | 2026-06-02 | 2026-06-13 |  |  | 2026-06-12 | DONE: perfect-maze generator, 225 nodes / 224 edges, fully connected (Step 1). | 12272268107
Dynamic shifting-maze + earthquake telegraph |  | Gameplay | Juan | Juan Mosqueda | Done | Blue |  | 2026-06-02 | 2026-06-13 | Graph-based procedural maze generation (perfect maze) |  | 2026-06-12 | DONE: re-root shifting + earthquake telegraph; invariant held over 2000 shifts (Step 2 / MOTA-028). | 12272268108
Four differentiated NPCs (Bola, Mancha, Huracán, Conejo) — Anexo §3 |  | Gameplay | Juan | Juan Mosqueda | Done | Blue |  | 2026-06-02 | 2026-06-13 | Graph-based procedural maze generation (perfect maze) |  | 2026-06-12 | DONE: Bola/Mancha/Huracán/Conejo, differentiated FSMs (MOTA-023). | 12272268109
Dynamic navigation + pathfinding adapting to shift (graph traversal) — Anexo §3 |  | Gameplay | Juan | Juan Mosqueda | Done | Blue |  | 2026-06-02 | 2026-06-13 | Four differentiated NPCs (Bola, Mancha, Huracán, Conejo) — Anexo §3 |  | 2026-06-12 | DONE: MazeGraphPath graph traversal, recomputes on maze_shifted; NavigationAgent removed (Step 6c). | 12272268110
Interactions: status effects, Bola charge, Mancha bombs/smoke |  | Gameplay | Juan | Juan Mosqueda | Done | Blue |  | 2026-06-02 | 2026-06-13 | Four differentiated NPCs (Bola, Mancha, Huracán, Conejo) — Anexo §3 |  | 2026-06-12 | DONE: status states, Bola charge, Mancha bomb→smoke (MOTA-031/032/033). | 12272268111
Replay record/playback + viewer/picker (dev tooling) |  | Gameplay | Juan | Juan Mosqueda | Done | Blue |  | 2026-06-03 | 2026-06-14 | Dynamic shifting-maze + earthquake telegraph |  | 2026-06-12 | DONE: recorder + viewer + picker + follow camera (MOTA-035..041). | 12272254514
Headless simulation harness + engagement metrics (difficulty tuning) |  | Gameplay | Juan | Juan Mosqueda | Done | Blue |  | 2026-06-02 | 2026-06-13 | Four differentiated NPCs (Bola, Mancha, Huracán, Conejo) — Anexo §3 |  | 2026-06-12 | DONE: headless harness, Excel batch runner, NPC scoring modes, engagement metrics (MOTA-039..046). | 12272254515
Dev score overlay + 2-min round timer + per-contestant winner |  | Gameplay | Juan | Juan Mosqueda | Done | Blue | ★ CRITICAL | 2026-06-02 | 2026-06-13 | Graph-based procedural maze generation (perfect maze) |  | 2026-06-12 | DONE: dev overlay + round timer + per-contestant winner (MOTA-017..022). | 12272254516
GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  | Infra/DevOps | Saul | Saul Zavala Morin | Done | Blue |  | 2026-06-10 | 2026-06-13 |  |  | 2026-06-04 | DONE (by Juan): Firestore, BigQuery, Cloud Storage, Cloud IAM, service account game-api-backend, ADC impersonation, budget alerts. PENDING for Saul: RS256 keys, Cloud Run deploy, env split. | 12272254517
FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  | Backend Foundation | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-25 | 2026-06-26 | GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts, Client<->Backend REST API contract (endpoints, payloads, JWT, error codes) |  |  |  | 12272254518
RS256 keypair in Secret Manager + JWKS (.well-known) endpoint |  | Backend Foundation | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-29 | 2026-06-29 | FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  |  |  | 12272254519
Firestore users/sessions/revoked_jtis schema + Production-mode rules |  | Backend Foundation | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-29 | 2026-06-30 | FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  |  |  | 12272254520
Dev / Staging / Prod environments (project-per-env) + Terraform module |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-27 | 2026-06-28 | Environment & secrets design sign-off (dev/staging/prod topology), FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  |  |  | 12272254521
CI/CD: GitHub Actions + Artifact Registry single-image promotion pipeline |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-08 | 2026-07-09 | Dev / Staging / Prod environments (project-per-env) + Terraform module |  |  |  | 12272268267
Cloud Monitoring/alerts (5xx on auth & payments), logging, uptime, Pub/Sub kill switch |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-01 | 2026-07-02 | FastAPI service scaffold on Cloud Run (max-instances=10, ADC, health checks) |  |  |  | 12272268268
POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-06 | 2026-07-07 | Firestore users/sessions/revoked_jtis schema + Production-mode rules, RS256 keypair in Secret Manager + JWKS (.well-known) endpoint |  |  |  | 12272268269
/auth/refresh rotation + /auth/logout + JTI revocation; pending-callback poll |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-10 | 2026-07-13 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272121944
DELETE /auth/account — full erase + BigQuery deletion queue (GDPR / Apple 5.1.1) |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-14 | 2026-07-15 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions), POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272121945
HTTPS App Links (assetlinks.json) / Universal Links (AASA) hosting for OAuth callback |  | Auth Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-14 | 2026-07-14 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272121946
Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator |  | Client Foundation | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-06-25 | 2026-06-26 | Client infra layer: Events bus, Services locator, resources, node FSM, Client<->Backend REST API contract (endpoints, payloads, JWT, error codes) |  |  |  | 12272121947
Auth UI + Google sign-in client flow (OS.shell_open, callback poll) |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-22 | 2026-07-23 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator, POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272121948
Build flavors: dev/staging/prod export presets (API base, Firebase, AdMob IDs) |  | Client Release | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-16 | 2026-07-20 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator, Dev / Staging / Prod environments (project-per-env) + Terraform module |  |  |  | 12272121950
LevelData resource + LevelManager autoload (data-driven, 30 levels) — Anexo §2 |  | Gameplay | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-03 | 2026-07-06 | Dev score overlay + 2-min round timer + per-contestant winner |  |  |  | 12272122012
Win/lose conditions per LevelData (collect-all / score / survive) |  | Gameplay | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-14 | 2026-07-15 | LevelData resource + LevelManager autoload (data-driven, 30 levels) — Anexo §2 |  |  |  | 12272122013
ScoreSystem (real, persisted-ready) replacing temp HUD — Anexo §2 |  | Gameplay | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-14 | 2026-07-15 | LevelData resource + LevelManager autoload (data-driven, 30 levels) — Anexo §2 |  |  |  | 12272122014
Author & balance 30 levels (.tres) via simulation batches — Anexo §2 balance |  | Gameplay | Juan | Juan Mosqueda | In Progress | Green |  | 2026-07-16 | 2026-07-23 | Headless simulation harness + engagement metrics (difficulty tuning), Win/lose conditions per LevelData (collect-all / score / survive), ScoreSystem (real, persisted-ready) replacing temp HUD — Anexo §2 | 2026-06-12 |  | DONE: simulation/balancing engine — headless harness + Excel batch runner + NPC scoring + engagement/difficulty metrics. PENDING: author the 30 LevelData .tres and run balancing passes to hit target win-rate/star thresholds. | 12272122015
Level-select scene (locked/stars, Events-driven) |  | Gameplay | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-07-27 | 2026-07-28 | Real player HUD (lives, score, level, pause) — separate from dev overlay, LevelData resource + LevelManager autoload (data-driven, 30 levels) — Anexo §2 |  |  |  | 12272122016
ProgressionService client (consumes /progress, server-authoritative) |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-03 | 2026-08-04 | Backend /progress + POST /progress/level-complete (server-validated unlock/score), Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator |  |  |  | 12272122017
Backend /progress + POST /progress/level-complete (server-validated unlock/score) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-15 | 2026-07-16 | Firestore users/sessions/revoked_jtis schema + Production-mode rules, POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272122018
Backend /lives (server-authoritative regen) + /lives/spend + config — Anexo §4 |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-16 | 2026-07-17 | Firestore users/sessions/revoked_jtis schema + Production-mode rules, POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272122019
Backend /lives/grant (iap / rewarded_ad SSV / promo) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-23 | 2026-07-24 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator, Backend /lives (server-authoritative regen) + /lives/spend + config — Anexo §4 |  |  |  | 12272122020
LivesService client (consumes /lives) + lives HUD widget — Anexo §4 |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-04 | 2026-08-05 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair, Backend /lives (server-authoritative regen) + /lives/spend + config — Anexo §4 |  |  |  | 12272135332
Out-of-lives modal (wait / watch rewarded / buy life pack) |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-19 | 2026-08-20 | LivesService client (consumes /lives) + lives HUD widget — Anexo §4, Store UI scene (server-resolved catalog, direct-price only, no gacha) — Anexo §5 |  |  |  | 12272135333
Placeholder UI/menu skeleton + screen navigation flow (unblocks integration) |  | Client UX | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-07-03 | 2026-07-06 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator, Client infra layer: Events bus, Services locator, resources, node FSM |  |  | Stand up placeholder scenes (menu, level-select, store, HUD, modals) + navigation flow so Saul can wire and test API calls against real screens before final art/UX land. | 12272135334
Real player HUD (lives, score, level, pause) — separate from dev overlay |  | Client UX | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-07-20 | 2026-07-21 | ScoreSystem (real, persisted-ready) replacing temp HUD — Anexo §2, Placeholder UI/menu skeleton + screen navigation flow (unblocks integration) |  |  |  | 12272135335
Main menu, settings, profile & account screens (incl. account deletion UI) |  | Client UX | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-03 | 2026-08-04 | Auth UI + Google sign-in client flow (OS.shell_open, callback poll), Placeholder UI/menu skeleton + screen navigation flow (unblocks integration) |  |  |  | 12272133959
First-levels onboarding/tutorial (teach movement, shifting, evasion) |  | Client UX | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-07-30 | 2026-07-31 | Real player HUD (lives, score, level, pause) — separate from dev overlay, Onboarding/tutorial script + first-time-user copy, tips & objective framing, Author & balance 30 levels (.tres) via simulation batches — Anexo §2 balance |  |  |  | 12272133960
Backend /store/catalog + promotions (server-resolved, audience-segmented) — Anexo §5 |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-23 | 2026-07-24 | Backend /progress + POST /progress/level-complete (server-validated unlock/score), Firestore users/sessions/revoked_jtis schema + Production-mode rules |  |  |  | 12272133961
Store UI scene (server-resolved catalog, direct-price only, no gacha) — Anexo §5 |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-17 | 2026-08-18 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair, Backend /store/catalog + promotions (server-resolved, audience-segmented) — Anexo §5 |  |  |  | 12272133962
Skins equip/select UI + /profile/equip-skin + boot-apply equipped skin — Anexo §5 |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-19 | 2026-08-20 | Store UI scene (server-resolved catalog, direct-price only, no gacha) — Anexo §5, Backend /profile/equip-skin (entitlement-checked) + equipped_skin persistence |  |  |  | 12272133963
Backend /profile/equip-skin (entitlement-checked) + equipped_skin persistence |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-29 | 2026-07-29 | Backend /store/catalog + promotions (server-resolved, audience-segmented) — Anexo §5 |  |  |  | 12272254774
Remote Config for level/lives/catalog tunables (live-tunable, no app update) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-30 | 2026-07-31 | Backend /store/catalog + promotions (server-resolved, audience-segmented) — Anexo §5 |  |  |  | 12272254775
Enable Google Play Developer API (24h activation — Day 1) + Play Console SA invite |  | External Services | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-15 | 2026-06-15 | GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  |  |  | 12272254776
POST /payments/android/verify (verify -> grant -> acknowledge/consume, replay-safe) |  | Payments Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-07 | 2026-07-08 | Firestore users/sessions/revoked_jtis schema + Production-mode rules, Enable Google Play Developer API (24h activation — Day 1) + Play Console SA invite |  |  |  | 12272254777
Daily reconciliation job (Cloud Scheduler): pending verify + refund detection |  | Payments Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-20 | 2026-07-21 | POST /payments/android/verify (verify -> grant -> acknowledge/consume, replay-safe) |  |  |  | 12272254779
Refund notifications (Play Pub/Sub + Apple ASSN v2) endpoints |  | Payments Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-22 | 2026-07-22 | POST /payments/android/verify (verify -> grant -> acknowledge/consume, replay-safe) |  |  |  | 12272254780
IAP client integration (Play Billing + StoreKit 2 plugins) via Services.payments |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-23 | 2026-07-24 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator, POST /payments/android/verify (verify -> grant -> acknowledge/consume, replay-safe) |  |  |  | 12272254781
AdMob account + ad units (rewarded/interstitial/banner) + test IDs |  | External Services | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-16 | 2026-06-17 | GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  |  |  | 12272254782
AdMob client integration + SDK init order (consent -> ATT -> init) via Services.ads |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-07 | 2026-07-09 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator, AdMob account + ad units (rewarded/interstitial/banner) + test IDs |  |  |  | 12272268493
"No Ads" IAP wiring + entitlement check on startup |  | Client Systems | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-06 | 2026-08-06 | IAP client integration (Play Billing + StoreKit 2 plugins) via Services.payments, AdMob client integration + SDK init order (consent -> ATT -> init) via Services.ads |  |  |  | 12272268496
Final art: Bola, Mancha, Huracán (replace placeholder sprites) — media pipeline |  | Assets | Juan | Juan Mosqueda | Not Started | Amber |  | 2026-06-15 | 2026-06-18 | Four differentiated NPCs (Bola, Mancha, Huracán, Conejo) — Anexo §3 |  |  |  | 12272268497
Final art: Rabbit / Conejo (replace placeholder) |  | Assets | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-10 | 2026-07-13 | Final art: Bola, Mancha, Huracán (replace placeholder sprites) — media pipeline |  |  |  | 12272268498
Skin assets (skin_gold, skin_silver) + atlas/game-ready export |  | Assets | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-10 | 2026-07-13 | Final art: Bola, Mancha, Huracán (replace placeholder sprites) — media pipeline |  |  |  | 12272268499
UI kit art: HUD, store, menus, modals |  | Assets | Juan | Juan Mosqueda | Not Started | Amber |  | 2026-06-15 | 2026-06-17 | Client infra layer: Events bus, Services locator, resources, node FSM |  |  |  | 12272094732
Audio direction & sound palette (style refs, mix targets, per-tier mood) |  | Assets (Audio) | Juan | Juan Mosqueda | Not Started | Amber |  | 2026-06-18 | 2026-06-19 | Project plan, milestones & RACI agreed (this workbook) |  |  |  | 12272094735
Music: main theme + in-level loops (intro/mid/late tiers) + menu track |  | Assets (Audio) | Juan | Juan Mosqueda | Not Started | Amber |  | 2026-06-20 | 2026-06-25 | Audio direction & sound palette (style refs, mix targets, per-tier mood) |  |  |  | 12272094737
SFX: collect, maze-shift/earthquake, Bola charge, Mancha bomb, UI, win/lose |  | Assets (Audio) | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-06-29 | 2026-07-02 | Audio direction & sound palette (style refs, mix targets, per-tier mood) |  |  |  | 12272094739
Character voices / vocalizations (Mota + 4 NPC barks & stingers) |  | Assets (Audio) | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-06-29 | 2026-07-01 | Audio direction & sound palette (style refs, mix targets, per-tier mood) |  |  |  | 12272094741
Audio integration in Godot (AudioStreamPlayer buses, mix, ducking, settings toggle) |  | Client UX | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-07-22 | 2026-07-23 | Music: main theme + in-level loops (intro/mid/late tiers) + menu track, Character voices / vocalizations (Mota + 4 NPC barks & stingers), SFX: collect, maze-shift/earthquake, Bola charge, Mancha bomb, UI, win/lose, Real player HUD (lives, score, level, pause) — separate from dev overlay |  |  |  | 12272094743
Narrative bible: world/character lore tie-in for the 30-level arc (roster incl. Zas) |  | Narrative | Juan | Juan Mosqueda | Not Started | Amber |  | 2026-06-18 | 2026-06-19 | Project plan, milestones & RACI agreed (this workbook) |  |  |  | 12272094745
Level progression narrative beats (intro/mid/late arc framing across 30 levels) |  | Narrative | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-14 | 2026-07-15 | LevelData resource + LevelManager autoload (data-driven, 30 levels) — Anexo §2, Narrative bible: world/character lore tie-in for the 30-level arc (roster incl. Zas) |  |  |  | 12272094747
Onboarding/tutorial script + first-time-user copy, tips & objective framing |  | Narrative | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-21 | 2026-07-22 | Level progression narrative beats (intro/mid/late arc framing across 30 levels) |  |  |  | 12272094749
In-game copy + localization-ready strings (UI/store/modals), EN + PT-BR/ES-LATAM |  | Narrative | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-31 | 2026-08-03 | Onboarding/tutorial script + first-time-user copy, tips & objective framing |  |  |  | 12272094751
BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions) |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Amber |  | 2026-06-18 | 2026-06-19 | GCP base infra: Firestore, BigQuery, Cloud Storage, Cloud IAM, budget alerts |  |  |  | 12272094753
Firestore -> BigQuery async streaming (off hot path) + dedup keys |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-22 | 2026-06-23 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions) |  |  |  | 12272094755
Ad-revenue reconciliation: custom impression event + AdMob Reporting API daily job |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-10 | 2026-07-13 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions), AdMob client integration + SDK init order (consent -> ATT -> init) via Services.ads |  |  |  | 12272094757
Looker Studio dashboards: retention, per-region/per-age revenue, KPI gates |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-02 | 2026-07-03 | Firestore -> BigQuery async streaming (off hot path) + dedup keys |  |  |  | 12272094760
Firebase Crashlytics integration (client) — before any mobile testing |  | Client Release | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-07 | 2026-07-09 | Godot HTTP API client service (REST, JWT store/refresh, retry) via Services locator |  |  |  | 12272094806
Tenjin SDK integration (client) + backend fraud filtering (before first paid UA) |  | External Services | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-06-24 | 2026-06-26 | BigQuery analytics tables (login/session/behavior/purchase/ad/entitlement/deletions) |  |  |  | 12272094807
Vertical-slice playtest build (core loop + ~8-10 levels + HUD + onboarding + audio) |  | Client Release | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-08-12 | 2026-08-17 | Level-select scene (locked/stars, Events-driven), Audio integration in Godot (AudioStreamPlayer buses, mix, ducking, settings toggle), First-levels onboarding/tutorial (teach movement, shifting, evasion), ScoreSystem (real, persisted-ready) replacing temp HUD — Anexo §2 |  |  |  | 12272094808
Recruit ~30-40 playtesters (network/friends-and-family) + feedback survey + light consent |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-06-22 | 2026-06-26 | Project plan, milestones & RACI agreed (this workbook) |  |  |  | 12272094809
Distribute mini-launch build (Play internal track / TestFlight) to testers |  | Client Release | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-08-18 | 2026-08-18 | Vertical-slice playtest build (core loop + ~8-10 levels + HUD + onboarding + audio), Recruit ~30-40 playtesters (network/friends-and-family) + feedback survey + light consent |  |  |  | 12272094810
Collect & synthesize feedback (survey + watch sessions) -> prioritized change list |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-08-19 | 2026-08-25 | Distribute mini-launch build (Play internal track / TestFlight) to testers |  |  |  | 12272094811
Pre-Alpha polish from playtest feedback (gameplay/onboarding/difficulty fixes) |  | Gameplay | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-08-26 | 2026-08-27 | Collect & synthesize feedback (survey + watch sessions) -> prioritized change list |  |  |  | 12272175642
Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-17 | 2026-07-22 | POST /auth/login — Google OAuth verify, upsert user, issue JWT pair |  |  |  | 12272175643
Verifiable parental consent (email-plus) flow — backend + client UI |  | Compliance | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-08-05 | 2026-08-11 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags, Auth UI + Google sign-in client flow (OS.shell_open, callback poll) |  |  |  | 12272094534
Brazil age assurance: app-store/OS age signals (Apple Declared Age Range / Play) |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-23 | 2026-07-27 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  |  |  | 12272094535
CCPA opt-out: in-app UI + Firestore persistence + RDP flag in AdMob init |  | Compliance | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-08-05 | 2026-08-07 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags, AdMob client integration + SDK init order (consent -> ATT -> init) via Services.ads |  |  |  | 12272094536
Monthly recalc Cloud Function (age threshold crossing, per-user country) |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-27 | 2026-07-28 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  |  |  | 12272094537
Privacy Policy + Terms (EN + PT-BR) hosted; Data Safety + Privacy Nutrition labels |  | Compliance | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-08-10 | 2026-08-14 | Region-aware age logic: consent_age_threshold (US13/BR18) + protection flags |  |  |  | 12272094538
IARC rating (globalratings.com) + ClassInd mapping (BR 'Livre') |  | Compliance | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-08-17 | 2026-08-18 | Privacy Policy + Terms (EN + PT-BR) hosted; Data Safety + Privacy Nutrition labels |  |  |  | 12272094539
Firebase Test Lab runs on 30+ physical devices (crash-free gate) |  | Client Release | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-07 | 2026-08-13 | AdMob client integration + SDK init order (consent -> ATT -> init) via Services.ads, Author & balance 30 levels (.tres) via simulation batches — Anexo §2 balance, IAP client integration (Play Billing + StoreKit 2 plugins) via Services.payments |  |  |  | 12272094540
Alpha internal build + technical validation (Fase Alpha gate) |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-08-31 | 2026-09-03 | MP Go/No-Go gate - playtest (agreed metrics), Firebase Test Lab runs on 30+ physical devices (crash-free gate), Pre-Alpha polish from playtest feedback (gameplay/onboarding/difficulty fixes) |  |  |  | 12272094541
Store assets: icon, screenshots, preview video (maze shifts in first 3s) |  | Assets | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-16 | 2026-07-17 | Skin assets (skin_gold, skin_silver) + atlas/game-ready export, UI kit art: HUD, store, menus, modals |  |  |  | 12272094542
ASO + localized store listings (Brazilian PT + LATAM ES) |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-24 | 2026-07-29 | Store assets: icon, screenshots, preview video (maze shifts in first 3s) |  |  |  | 12272175996
Upgrade Firebase to Blaze (2 weeks before launch) + prod secrets/bindings |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-02 | 2026-07-02 | Dev / Staging / Prod environments (project-per-env) + Terraform module |  |  |  | 12272175997
Android closed/open test tracks (Play Console) — Beta build |  | Client Release | Juan | Juan Mosqueda | Not Started | Gray | ★ CRITICAL | 2026-09-04 | 2026-09-08 | IARC rating (globalratings.com) + ClassInd mapping (BR 'Livre'), Alpha internal build + technical validation (Fase Alpha gate) |  |  |  | 12272175998
Closed beta with Discord cohort (crash <1%, flows functional) — Beta gate |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-09 | 2026-09-17 | Android closed/open test tracks (Play Console) — Beta build, Stand up Discord server (structure per plan §4.1) + roles |  |  |  | 12272176000
Stand up Discord server (structure per plan §4.1) + roles |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-06-22 | 2026-06-24 | Project plan, milestones & RACI agreed (this workbook) |  |  |  | 12272176003
Discord bot privacy policy + Message Content intent prep |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-01 | 2026-07-02 | Stand up Discord server (structure per plan §4.1) + roles |  |  |  | 12272176004
In-game -> Discord entry points + invite/rematch links |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-08-14 | 2026-08-18 | Stand up Discord server (structure per plan §4.1) + roles, Main menu, settings, profile & account screens (incl. account deletion UI) |  |  |  | 12272094779
TikTok/Reels creative engine (AI-generated, human-approved, AI-disclosure label) |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-18 | 2026-07-25 | Store assets: icon, screenshots, preview video (maze shifts in first 3s) |  |  |  | 12272094781
Recruit 100-500 closed-beta cohort (Discord + Reddit seeding) |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-07-02 | 2026-07-13 | Stand up Discord server (structure per plan §4.1) + roles |  |  |  | 12272094734
Community insight pipeline: self-hosted model in tenant, de-identified aggregates |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-07-03 | 2026-07-06 | Firestore -> BigQuery async streaming (off hot path) + dedup keys, Stand up Discord server (structure per plan §4.1) + roles |  |  |  | 12272094736
Release Candidate build + critical-issue burn-down + operational validation |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-10 | 2026-09-13 | Alpha/Beta Go/No-Go gate (agreed metrics), Closed beta with Discord cohort (crash <1%, flows functional) — Beta gate |  |  |  | 12272094738
Soft launch LATAM (Brazil + Mexico) — production deploy |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-25 | 2026-09-29 | Release Candidate build + critical-issue burn-down + operational validation, Privacy Policy + Terms (EN + PT-BR) hosted; Data Safety + Privacy Nutrition labels, Upgrade Firebase to Blaze (2 weeks before launch) + prod secrets/bindings, Brazil age assurance: app-store/OS age signals (Apple Declared Age Range / Play) |  |  |  | 12272094740
Google App Campaigns LATAM (surgical paid) + Tenjin fraud filter live |  | Community | Juan | Juan Mosqueda | Not Started | Gray |  | 2026-10-11 | 2026-10-17 | Tenjin SDK integration (client) + backend fraud filtering (before first paid UA), Soft launch LATAM (Brazil + Mexico) — production deploy |  |  |  | 12272094742
Monitor kill-criteria (D1>=25-30%, D7>=10%, No-Ads 2-5%, LTV>cost) on dashboards |  | Dataflow & Outputs | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-10-11 | 2026-10-17 | Looker Studio dashboards: retention, per-region/per-age revenue, KPI gates, Soft launch LATAM (Brazil + Mexico) — production deploy |  |  |  | 12272094744
Live balance/economy tuning via Remote Config (levels, lives, promotions) |  | Game Services Backend | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-10-13 | 2026-10-18 | Soft launch LATAM (Brazil + Mexico) — production deploy, Remote Config for level/lives/catalog tunables (live-tunable, no app update) |  |  |  | 12272094746
Stability + monetization + retention soft-launch testing (Fase Beta/Soft Launch) |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-10-06 | 2026-10-19 | Soft launch LATAM (Brazil + Mexico) — production deploy |  |  |  | 12272094748
Soft-launch kill-criteria review + go/no-go (LA EMPRESA discretion) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-10-31 | 2026-11-01 | Stability + monetization + retention soft-launch testing (Fase Beta/Soft Launch), Monitor kill-criteria (D1>=25-30%, D7>=10%, No-Ads 2-5%, LTV>cost) on dashboards |  |  |  | 12272094750
Commercial launch readiness checklist sign-off (no-go items cleared) |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-11-02 | 2026-11-06 | Soft-launch kill-criteria review + go/no-go (LA EMPRESA discretion) |  |  |  | 12272094752
Official LATAM commercial launch (Fase 4) — full production release |  | Client Release | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-11-07 | 2026-11-09 | Commercial launch readiness checklist sign-off (no-go items cleared) |  |  |  | 12272094754
Post-launch operations runbook + on-call (2-yr support obligation begins) |  | Infra/DevOps | Saul | Saul Zavala Morin | Not Started | Gray |  | 2026-11-10 | 2026-11-10 | Official LATAM commercial launch (Fase 4) — full production release |  |  |  | 12272094756
Technical documentation pass (systems, integrations, architecture) — Anexo §7 |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray |  | 2026-11-10 | 2026-11-15 | Official LATAM commercial launch (Fase 4) — full production release |  |  |  | 12272094759
Alpha/Beta Go/No-Go gate (agreed metrics) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-09-18 | 2026-09-18 | Closed beta with Discord cohort (crash <1%, flows functional) — Beta gate |  |  |  | 12275380968
MP Go/No-Go gate - playtest (agreed metrics) |  | Planning | Juan+Saul | Juan Mosqueda, Saul Zavala Morin | Not Started | Gray | ★ CRITICAL | 2026-08-28 | 2026-08-28 | Pre-Alpha polish from playtest feedback (gameplay/onboarding/difficulty fixes) |  |  |  | 12275387415
[8 empty] | 2026-06-01 | 2026-11-15 |  | 2026-06-12 to 2026-06-14 | 2026-06-04 to 2026-06-12